## Slide 1
SHELTER / CCCM SECTOR · COX’S BAZAR
Mid-year performance and funding review
January – June 2026 · 5W reporting from 34 camps · prepared by Sector Information Management
Purpose: agree where the sector is off track at mid-year, and what the sector decides to do about it before the monsoon peak.
Notes: Mid-year review built from the consolidated SCCCM 5W dataset for January to June 2026, compared against the 2026 JRP log frame targets and the sector funding position.

## Slide 2
At a glance — mid-year 2026
Half the year is gone. Pro-rata, the sector should be at roughly 50% of every annual target.
SCCCM Sector · Coordination Meeting · Mid-year review, January–June 2026
1.25M
People covered by site coordination
100% of the annual target — full coverage maintained
42%
Of USD 128M funding received
USD 74.2M gap at mid-year
40%
Shelter households reached
61,210 of 153,025 — 10 points behind pro-rata
35%
NFI households reached
66,519 of 190,053 — 15 points behind
What the dataset covers
15,519 validated 5W records, January to June 2026
34 refugee camps including Bhasan Char — full geographic coverage
11 activity groups and 82 sub-activities from the 2026 JRP log frame
Reported monthly by appealing and implementing partners; consolidated by Sector IM
What it is compared against
2026 JRP log frame — annual targets by output indicator
RCP 2026 4W activity matrix — activity groups and priority levels
JRP 2026 funding analysis, updated to 30 June
Benchmark: 50% of the annual target at the six-month point
Notes: The 50% pro-rata benchmark is the simplest fair test at mid-year. It is not a rule — seasonal activities legitimately deviate — but any indicator far from it needs an explanation.

## Slide 3
Achievement against annual target
Percentage of the 2026 JRP target delivered by 30 June. Anything below the 50% line is behind schedule.
SCCCM Sector · Coordination Meeting · Mid-year review, January–June 2026
Chart: 
| Site coordination coverage | Shelter assistance - refugee HH | Energy / LPG support | NFI assistance | Emergency NFI and LPG | Emergency shelter | Complaints resolved - AAP | Community participation | Capacity sharing initiatives
% of annual target | 100 | 40 | 53.5 | 35 | 10.7 | 17.9 | 51 | 41.6 | 52
Reading this
Coordination and coverage functions are at 100% — these are services to the whole population.
Material assistance is 10 to 15 points behind pro-rata.
The two emergency indicators — emergency shelter at 18% and emergency NFI/LPG at 11% — are the sharpest.
Host community shelter (target 9,591 HH) has no delivery reported at all.
Emergency preparedness stocks are at 11–18% of target with the monsoon peak in July. This is the single most time-critical gap on this slide.
Notes: Host community delivery is zero in this dataset because it is reported under Location = Host Community, which is outside this extract. That is a reporting boundary, not necessarily zero delivery — it must be confirmed with partners.

## Slide 4
Delivery is slowing month on month
Households reached per month across all activity groups, January to June 2026.
SCCCM Sector · Coordination Meeting · Mid-year review, January–June 2026
Chart: 
| January | February | March | April | May | June
Households reached | 72202 | 72559 | 68946 | 65559 | 53409 | 49184
-32%
June against January
Monthly household delivery
The fall begins in May, not June — it tracks funding availability, not the weather.
LPG delivery held steady; shelter and NFI carried almost all of the decline.
At the June run rate the sector lands near 70% of the shelter target, not 100%.
Notes: Projection: six more months at the June rate gives roughly 61,210 + 6 x 49,184 household-activities, which for shelter alone lands near 70 per cent of the annual target.

## Slide 5
Where the delivery sits
Households reached by activity group, January to June 2026 (household-unit activities only).
SCCCM Sector · Coordination Meeting · Mid-year review, January–June 2026
Chart: 
| LPG | NFI | Shelter | DRM-SNFI | DRM-SM
Households reached | 148000 | 66519 | 61210 | 60600 | 45530
The unit problem
These five groups report in households. The other six report in metres, hectares, camps, sessions or cases.
A single "total reached" figure across the sector would mix all of them and mean nothing.
Each indicator is therefore reported in its own unit, exactly as the log frame defines it.
Households are not de-duplicated across activity groups — one household receiving both NFI and LPG appears twice. Unique-household reach requires a separate calculation, not a sum of this chart.
Notes: This is the most common misreading of the 5W. Always present activity-group totals as activities delivered, not as unique households.

## Slide 6
The gap is geographic
Shelter and NFI households reached per 1,000 people, January to June 2026 — eight lowest and five highest camps.
SCCCM Sector · Coordination Meeting · Mid-year review, January–June 2026
Chart: 
| Camp 20 Extension | Camp 25 | Camp 4 Extension | Bhasan Char | Camp 21 | Camp 27 | Camp 24 | Camp 13 | Camp 16 | Camp 7 | Camp 15 | Camp 12 | Camp 8W
HH per 1,000 people | 44.2 | 48.9 | 55.8 | 56.5 | 65.4 | 70.7 | 73.2 | 76.5 | 122.4 | 123.9 | 127.7 | 135.9 | 140.5
3.2×
Spread between camps
Highest-served camp against lowest-served camp
Camp 20 Extension, Camp 25 and Camp 4 Extension are at under half the sector average.
Bhasan Char sits in the bottom four despite a population of 47,000.
Camp 24 and Camp 13 are large camps in the bottom eight — this is not only a small-camp problem.
Population is controlled for: this is delivery per head, not raw volume.
Notes: Per-capita normalisation is what makes this actionable. Raw household counts would simply rank camps by size.

## Slide 7
The same camps are also missing emergency capacity
Camps without the capacity in place as at 30 June 2026 — counted as distinct camps, not summed across months.
SCCCM Sector · Coordination Meeting · Mid-year review, January–June 2026
Trained DRM first responders
28 of 34 camps
Missing: Bhasan Char, Camp 20 Extension, Camp 21, Camp 25, Camp 27, Camp 4 Extension
82%
Established fire response capacity
31 of 34 camps
Missing: Bhasan Char, Camp 20 Extension, Camp 25
91%
Functioning complaints mechanism (CFRM)
30 of 34 camps
Missing: Camp 20, Camp 20 Extension, Camp 25, Camp 4 Extension
88%
Camp 20 Extension and Camp 25 appear on all three lists and in the bottom three for delivery. They are the sector’s clearest combined gap.
Counting note: capacity indicators are counted as distinct camps. Summing the monthly 5W rows would report 168 camps out of 34.
Notes: This is a standard 5W trap: monthly reporting of a camp-level status indicator double counts if summed. Always de-duplicate to distinct camps.

## Slide 8
Funding position — JRP 2026, as at 30 June
USD 128 million required for the sector. 42% received, leaving a gap of USD 74.2 million.
SCCCM Sector · Coordination Meeting · Mid-year review, January–June 2026
Chart: 
| Funded | Gap
Funding | 42 | 58
42%
funded
Chart: 
| Shelter | DRM | NFI | Access & Safety | Slope stabilisation | LPG (to year end)
Funding gap (USD million) | 24.6 | 15.8 | 11.2 | 7.6 | 11.2 | 10.1
Priority-level position
P1 + P2 combined gap USD 65.4M — P2 activities only 15.5% funded.
P3 + Reserve/Standby gap USD 9.2M; Reserve/Standby only 16.6% funded.
Site management support: 6.3% funded (USD 280K) — the function delivering 100% coverage.
NFI replenishment 13.2% funded; stock covers needs only to the end of Q2.
Notes: Figures carried forward from the JRP 2026 funding analysis presented at the April sector meeting and updated to the 30 June reporting point.

## Slide 9
Where delivery and funding disagree
Two findings that only appear when the 5W and the funding data are read together.
SCCCM Sector · Coordination Meeting · Mid-year review, January–June 2026
Delivering on almost no funding
Site coordination and site management support reports 100% population coverage while funded at 6.3% — USD 280,000 against a requirement of USD 4.4M.
Full coverage today is being carried by partner cost-sharing, not by the appeal. It is the least visible risk in the portfolio and the fastest to collapse.
Funded work not converting into delivery
Slope stabilisation: 43,208 sq m completed against 427,212 sq m identified — 10.1%, with a 63% funding gap and the monsoon peak in July.
At least 34,000 shelters and around 163,000 people sit in areas identified as high-risk and not yet stabilised.
What this means for prioritisation
Coverage figures alone would say the sector is performing. Funding figures alone would say it is failing. Neither is the whole picture.
The sector should protect the two functions where a small amount of money holds up a large amount of coverage: site management support and emergency prepositioning.
Where funding exists but delivery lags — slope stabilisation — the constraint is implementation capacity and season, so re-tendering or reallocating before July is the live decision.
Notes: This slide is the reason the IM function sits in the meeting: neither dataset answers the question on its own.

## Slide 10
Monsoon and cyclone readiness — the time-critical gap
Emergency preparedness indicators at the six-month point, against the July rainfall peak.
SCCCM Sector · Coordination Meeting · Mid-year review, January–June 2026
Chart: 
| Emergency NFI and LPG (OUT6c) | Emergency shelter (OUT6d) | Slope stabilisation (sq m) | Camps with fire response capacity | Camps with DRM first responders
% of target in place | 11 | 18 | 10 | 91 | 82
34,000
Shelters in unstabilised high-risk areas
approximately 163,000 people
Prepositioned shelter and NFI kits cover a fraction of the caseload the multi-hazard plan assumes.
Three camps have no established fire response capacity, including Bhasan Char.
Six camps have no trained DRM first responders.
If a cyclone or major fire occurs in July, the sector can coordinate the response but cannot currently supply it at the scale the contingency plan assumes.
Notes: Aligned to the SOP for Cyclone Emergency Preparedness and Response and the Multi-Hazard Response Plan.

## Slide 11
What this dataset cannot yet tell us
Four limitations that affect how these figures should be read, and what Sector IM is doing about each.
SCCCM Sector · Coordination Meeting · Mid-year review, January–June 2026
Host community delivery is invisible
All 15,519 records are reported under Location = Refugee Camp. The host community shelter target of 9,591 households shows as zero. Confirming actual delivery with partners before the RCP submission.
Households are not de-duplicated
A household receiving NFI and LPG counts in both. Unique reach needs a household-level identifier the 5W does not carry; reported as activities delivered until then.
Mixed units in one column
Households, individuals, metres, hectares, camps and cases share the Reached column. Every figure here is reported in its own unit; a single sector total would be meaningless.
Camp-status indicators repeat monthly
Counted as distinct camps, not summed. Summing gives 168 camps out of 34. Proposing a status-type flag in the template for the next cycle.
None of these change the direction of the findings. They change how precisely each figure can be quoted outside this room.
Notes: Stating limitations before someone else finds them is what protects the sector figure when it is quoted by RCP or a donor.

## Slide 12
Key messages
SCCCM Sector · Coordination Meeting · Mid-year review, January–June 2026
1
Coverage is holding; assistance is not.
Site coordination reaches 100% of the population, but shelter is at 40% and NFI at 35% of their annual targets at the halfway point.
2
The slowdown started in May.
Monthly household delivery has fallen 32% since January, tracking funding availability rather than season. At the June rate the sector lands near 70% of the shelter target.
3
The gap is geographic and it compounds.
A 3.2-fold spread between camps, and the six lowest-delivery camps are largely the same camps missing DRM first responders and a functioning CFRM.
4
Emergency preparedness is the time-critical risk.
Emergency shelter at 18% and emergency NFI/LPG at 11% of target, slope stabilisation at 10%, with the rainfall peak in July.
5
A small amount of money holds up a large amount of coverage.
Site management support is 6.3% funded and delivering full coverage. It is the cheapest thing to protect and the most expensive to lose.
Notes: Five messages, in the order the evidence was presented.

## Slide 13
Decisions requested from the sector
Five decisions the Sector Coordinators and SAG are asked to take today.
SCCCM Sector · Coordination Meeting · Mid-year review, January–June 2026
1
Reallocate shelter and NFI delivery towards the eight lowest-coverage camps for Q3, with Camp 20 Extension, Camp 25, Camp 4 Extension and Bhasan Char treated as priority.
Shelter and NFI WGs, by 15 September
2
Bring forward emergency prepositioning before the July peak, and agree a minimum stock level per camp for shelter and NFI kits.
SAG, this week
3
Confirm host community delivery with partners and correct the reporting route before the RCP submission.
Sector IM with partners, by 10 September
4
Escalate site management support funding to the SAG and RCP as a coverage risk, not an administrative one — 6.3% funded against 100% delivery.
Sector Coordinators, immediately
5
Agree the July–December delivery plan against the revised run rate, or formally revise the shelter and NFI targets in the log frame.
SAG, by end September
Prepared by Sector Information Management from the consolidated SCCCM 5W (January–June 2026), the 2026 JRP log frame, the RCP 2026 4W activity matrix and the JRP 2026 funding analysis.
Notes: Each decision names an owner and a date. A decision without both is a discussion.