Post Distribution Monitoring (PDM) of NFI and Shelter assistance. It assumes data collection happens 4–8 weeks after the distribution, which is when PDMs usually take place, and covers both refugee and host community households.

a) Workplan, timeline and focal points

| # | Activity | Timeline | Lead focal point | Support |
| --- | --- | --- | --- | --- |
| 1 | Kick-off and Terms of Reference: agree the objectives, scope (camps, modality: in-kind or voucher), key questions and deadline | Week 1 (Days 1–2) | Shelter/NFI Sector Coordinator | Senior Management, IMO, AIMO |
| 2 | Secondary data review and sampling: collect distribution lists, define the sampling frame, calculate sample size (95% confidence, 5% margin of error, stratified by camp, modality and population group) | Week 1 (Days 2–5) | AIMO | IMO, partner M&E focal points |
| 3 | Tool design: questionnaire on receipt, timeliness, quality, use and sale of items, satisfaction, safety at the distribution point, feedback mechanism awareness and remaining needs; build it in KoboToolbox; translate it (Bangla/Rohingya) | Week 1–2 | AIMO | Shelter/NFI Technical Officer, Protection/AAP focal point, IMO |
| 4 | Pilot test and finalisation: test in 1–2 camps, then revise the wording, skip logic and form duration | Week 2 (Days 3–5) | AIMO | Field Officer, 2–3 enumerators |
| 5 | Enumerator training and logistics: methodology, informed consent, data protection, Kobo practice, safeguarding/PSEA, then enumerator deployment plan, devices and transport | Week 3 (Days 1–2) | Field/M&E Officer | AIMO (Kobo and data quality sessions), Protection |
| 6 | Data collection: household interviews plus key informant interviews or focus group discussions if needed | Week 3–4 (about 8–10 days) | Field Coordinators / partner teams | AIMO (daily quality monitoring), Camp focal points |
| 7 | Data cleaning and analysis: check duplicates, outliers and logic; weight results if needed; break down by sex, age, disability, camp and modality | Week 5 | AIMO | IMO (review) |
| 8 | Reporting and visualisation: draft report, Power BI dashboard, 2-page factsheet/infographic with recommendations | Week 5–6 | AIMO | IMO, Shelter/NFI Coordinator (technical review) |
| 9 | Validation and dissemination: present the findings to Senior Management and sector partners, agree on recommendations | Week 6 | Shelter/NFI Sector Coordinator | AIMO (presentation), IMO |
| 10 | Follow-up and archiving: action-point tracker; store the dataset securely; share an anonymised version | Week 6 onward | IMO | AIMO |

Key milestones:

- Week 2: tool finalised

- Week 4: data collection complete

- Week 5: preliminary findings to management

- Week 6: final report and dashboard

b) My role as AIMO in each activity

- Kick-off: Turn management's request into clear information needs and indicators, aligned with sector PDM standards and the Joint Response Plan (JRP) indicators. Check what distribution data already exists and point out any gaps.

- Sampling: Combine and clean the distribution lists from partners, calculate the sample size per stratum, and draw a random sample with replacements. Keep personal data protected and accessible only to those who need it.

- Tool design: Write the questionnaire with the technical and protection teams, then build it in Kobo as an XLSForm with skip logic, constraints, cascading camp lists and multiple languages. Make sure all results can be broken down by sex, age, disability, camp and modality.

- Pilot: Test the form in the field, review timings and data patterns, fix logic or wording problems, and deploy the final version.

- Training: Run the sessions on the Kobo app, consent scripts, data quality and data protection. Prepare the enumerator guide and the device setup.

- Data collection: Monitor progress every day against sample targets with a live tracker. Run quality checks (interview length, GPS location, missing or illogical answers) and give feedback to field teams within 24 hours.

- Cleaning and analysis: Clean the data, keeping a cleaning log for transparency. Analyse it in Excel, Power Query or R, and compare results against targets and earlier PDMs.

- Reporting: Produce the report, Power BI dashboard and infographic with clear key findings and practical recommendations, for example on item quality, distribution-point issues or unmet needs.

- Dissemination: Present the findings to management and partners, answer data questions, and record feedback and agreed actions.

- Follow-up: Keep the action tracker up to date and archive the tools, datasets and cleaning logs securely. Share the anonymised data and lessons learned so the next PDM can build on them.